## Sheet1
B&G Bus Tracking Application
Task ID | Task Name | Description | Assignee | Priority | Dependencies | Objective | Documentation Links
DB-001 | Define Database Schema | Design the overall database structure and identify all required tables with their attributes and data types. | Team A | High | None | Ensure a scalable and normalized database structure. | https://www.postgresql.org/docs/current/datatype.html
DB-002 | Create Users Table | Create a table to store user information, including fields for ID, name, email, password (hashed), and role. | Team B | High | DB-001 | Store all user-related data securely and efficiently. | https://www.postgresql.org/docs/current/sql-createtable.html
DB-003 | Create Buses Table | Create a table for storing bus details such as bus ID, license plate, and capacity. | Team B | Medium | DB-001 | Record and manage essential bus-related information. | https://www.postgresql.org/docs/current/sql-createtable.html
DB-004 | Create Routes Table | Design a table to store route details including route ID, name, and associated buses. | Team C | Medium | DB-001 | Manage all routes and their mapping to buses. | https://www.postgresql.org/docs/current/sql-createtable.html
DB-005 | Create Bus_Stops Table | Create a table to store bus stops with stop ID, name, GPS coordinates, and route association. | Team C | Medium | DB-004 | Keep a detailed list of all bus stops and their locations. | https://www.postgresql.org/docs/current/sql-createtable.html
DB-006 | Create Bus_Locations Table | Develop a table to record periodic GPS location updates for each bus, including timestamp and coordinates. | Team B | Medium | DB-003 | Enable tracking of real-time bus locations via GPS. | https://www.postgresql.org/docs/current/sql-createtable.html
DB-007 | Define Table Relationships | Establish foreign key relationships between tables (e.g., buses to routes, routes to stops). | Team A | High | DB-002, DB-003, DB-004 | Maintain referential integrity across the database. | https://www.postgresql.org/docs/current/ddl-constraints.html
DB-008 | Test and Optimize Queries | Write and run sample queries to test data retrieval, optimize indexing, and ensure performance. | Team D | High | DB-002, DB-006 | Ensure efficient queries for real-time data retrieval. | https://www.postgresql.org/docs/current/sql-explain.html